## ag-grid
Author | Project | Issue key | Issue summary | Work description | Started | Time spent
Đỗ Thành | TRAINING CALENDAR | CALENDAR-17 | Build image frontend ReactJS |  | Feb 26, 2024, 4:18 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-16 | Build image backend expressJS |  | Feb 26, 2024, 4:17 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-15 | Build image database postgres |  | Feb 26, 2024, 4:17 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-14 | Read requirment & split task |  | Feb 26, 2024, 4:16 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-13 | Setup Jira, timesheet for project |  | Feb 26, 2024, 4:16 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-12 | [FE] Read document about drag & drop library |  | Feb 26, 2024, 2:16 PM | 3h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-11 | [FE] Handle logic drag & drop for training session |  | Feb 26, 2024, 1:15 PM | 4h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-10 | [FE] Build ui & logic exercise card |  | Feb 26, 2024, 2:15 PM | 3h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-9 | [FE] Build ui & logic training session card |  | Feb 26, 2024, 2:14 PM | 3h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-8 | [FE] Build base redux saga, toolkit, axios |  | Feb 26, 2024, 4:13 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-7 | [BE] Build service updatePosition (drag & drop) |  | Feb 26, 2024, 2:12 PM | 3h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-6 | [FE] Build ui & logic calendar container, calendar column |  | Feb 26, 2024, 3:13 PM | 2h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-5 | [FE] Init project & structure |  | Feb 24, 2024, 3:58 PM | 1h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-3 | [BE] Build service for excercise |  | Feb 26, 2024, 3:12 PM | 2h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-2 | [BE] Build service for trainning_session |  | Feb 26, 2024, 3:11 PM | 2h
Đỗ Thành | TRAINING CALENDAR | CALENDAR-1 | [BE] Init Project & Database |  | Feb 26, 2024, 3:15 PM | 1h 20m
|  |  |  | _ |  | 30h 20m